Diploma of Leadership in Disability Services – Copyright License and Disclaimer Notice

Copyright

Copyright in this document and all the information it contains vests in the Department of Social Services on behalf of the Commonwealth.

Copyright notice — 2023

This document MPower108 Marketing Action plan review complete is licensed under the Creative Commons Attribution 4.0 International Licence

Licence URL: https://creativecommons.org/licenses/by/4.0/legalcode

Please attribute: © Commonwealth of Australia (Department of Social Services) 2023

Notice:

- If you create a derivative of this document, the Department of Social Services requests the following notice be placed on your derivative: Based on Commonwealth of Australia (Department of Social Services) data.

- Inquiries regarding this licence or any other use of this document are welcome. Please contact: Branch Manager, Communication Services Branch, Department of Social Services. Phone: 1300 653 227. Email: communications@dss.gov.au

Notice identifying other material or rights in this publication:

- Australian Commonwealth Coat of Arms — not Licensed under Creative Commons, see https://www.pmc.gov.au/government/commonwealth-coat-arms

- Certain images and photographs (as marked) — not licensed under Creative Commons

Disclaimer

This document is intended for educational purposes. The materials in the document may incorporate views, standards or recommendations of third parties or comprise materials contributed by third parties (third party materials). Such third party materials does not necessarily reflect the considered views of the Department of Social Services, or indicate a commitment to a particular course of action. The Department of Social Services makes no representation and accepts no responsibility for the accuracy, reliability, currency or completeness of any materials (including third party materials) contained in this document.

Further, the Department of Social Services disclaims all liability to any person in respect of anything, and of the consequences of anything, done or omitted to be done by any such person in reliance, whether wholly or partly, upon any information presented in this document.

The Department of Social Services makes available materials in this document on the understanding that it is not providing professional advice. Before relying on any of the materials in this document, users should obtain appropriate professional advice.

Views and recommendations of third parties, which may also be included in this document, do not necessarily reflect the views of the Department of Social Services, or indicate a commitment to a particular course of action. Links to other internet sites are for your convenience. These links do not constitute endorsement of materials at those sites, or any associated organisation, product or service.

# Action plan review

| Plan type | Marketing at the Sydney Disability expo |  |
| --- | --- | --- |
| Date | 30/11/2022 |  |
| Reviewed by | Ryan Cyan and Tammy White | Date of review:28/12/2022 |
| Issue/strategy | Comments |  |
| 1 | MPower108 has been experiencing a decline in customer service numbers, feedback provided has demonstrated the reputation of MPower108 is being impacted. The Marketing strategy for this activity is to boost the reputation of MPower108 Sydney through direct audience contact and to increase customer numbers. |  |

## Outcomes

| No. | Objectives | Measures of performance | Performance met (y/n) | Gaps or variations | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | Enhance the reputation of MPower108 Sydney | Increase in positive responses from feedback surveys before, during and after the marketing expo. | y |  | 50% of feedback surveys demonstrated an increase to the reputation of MPower108 Sydney as a quality service provider |
| 2 | Increase new customers to MPower108 Sydney services | An overall new customer increase of 3% (from 2038 current customers) | y | There was a .06% gap between the target performance metric and actual. | A total of 60 extra customer sign ups were achieved from the marketing event at the disability expo. This was an increase of 2.94% just under the 3% target. |

## Plan for achieving objectives

| Step by step plan | Due date | Name | Outcomes/variances | Completed date and signature |
| --- | --- | --- | --- | --- |
| Set the measurable performance goals to achieve from the marketing activity. | 20/10/2022 | Ryan Cyan and Tammy White | Performance goals were met with a slight negative of .06% in signups, however this was an overall achievement for the first-time event. | 20/10/2022 RCyan |
| Book booth for the disability expo, submitting organisational documents including insurances, etc | 22/10/2022 | Ryan Cyan and Tammy White | Completed on time. | 22/10/2022 RCyan |
| Work out skills and resources required for the event. Contact personnel who would be required for the expo (Rodney to select two other team members) | 20/10/2022 | Ryan Cyan and Tammy White | Completed on time. | 20/10/2022 RCyan |
| Event team meeting to discuss outcomes, requirements, budgets and expectations | 23/10/2022 | Ryan Cyan, team members, Lindy Lee and Tammy White | Completed late at 25/10/2022 due to other staff meetings. | 25/10/2022 RCyan |
| Marketing action plan for approval | 23/10/2022 | Ryan Cyan and Tammy White to Lindy Lee and Roman Brown | Completed and sent for approval from LLee. | 23/10/2022 RCyan |
| Order brochures, pamphlets and marketing materials to be published using MPower108 style guides and marketing resources | 26/10/2022 | Rodney Cyan and Lindy lee | Draft completed and sent for approval from LLee. Original MPower108 colours weren’t available so had to obtain approvals to amend. Approvals provided and amendments made. | 26/10/2022 RCyan, L Lee and T White |
| Plan the Exhibition Stand and Services | 27/10/2022 | Ryan Cyan and Tammy White | Completed | 27/10/2022 RCyan, L Lee and T White |
| Training on MPower108 services and presentations | 1/11/2022 | Ryan Cyan, team members Tammy White | Completed | 1/11/2022 RCyan, Tash, Nate and L Lee, T White |
| Carry Out Pre-Event Marketing via emails and social media for MPower108 | 23/11/2022 | Ryan Cyan and Tammy White and Lindy Lee | Completed | 23/11/2022 L Lee and T White |
| Create a feedback survey, checklist, review and follow up plan | 1-15 November 2022 | Ryan Cyan and Tammy White and Lindy Lee | Completed | 15/11/2022 RCyan, Tash, Nate and L Lee,- T White was absent due to illness. |
| Attend the expo and represent MPower108 | 30/11/2022 | Ryan Cyan, team members | Completed | 30/11/2022 RCyan, Tash, Nate |
| Compile and review feedback surveys along with review of the marketing action plan | 5/12/2022 | Ryan Cyan, team members to Tammy white and Roman Brown | Completed | 5/12/2022 RCyan, Tash, Nate |
| Send a report regarding marketing events and performance outcomes | 30/12/2022 | Ryan Cyan, team members to Tammy white and Roman Brown | Completed | 28/12/2022 RCyan, T White |
| Name: Ryan Cyan and Tammy White |  | 28/12/2022 | Signature: TWhite |  |