Diploma of Leadership in Disability Services – Copyright License and Disclaimer Notice

Copyright

Copyright in this document and all the information it contains vests in the Department of Social Services on behalf of the Commonwealth.

Copyright notice — 2023

This document MPower108 Operational action plan example is licensed under the Creative Commons Attribution 4.0 International Licence

Licence URL: https://creativecommons.org/licenses/by/4.0/legalcode

Please attribute: © Commonwealth of Australia (Department of Social Services) 2023

Notice:

- If you create a derivative of this document, the Department of Social Services requests the following notice be placed on your derivative: Based on Commonwealth of Australia (Department of Social Services) data.

- Inquiries regarding this licence or any other use of this document are welcome. Please contact: Branch Manager, Communication Services Branch, Department of Social Services. Phone: 1300 653 227. Email: communications@dss.gov.au

Notice identifying other material or rights in this publication:

- Australian Commonwealth Coat of Arms — not Licensed under Creative Commons, see https://www.pmc.gov.au/government/commonwealth-coat-arms

- Certain images and photographs (as marked) — not licensed under Creative Commons

Disclaimer

This document is intended for educational purposes. The materials in the document may incorporate views, standards or recommendations of third parties or comprise materials contributed by third parties (third party materials). Such third party materials does not necessarily reflect the considered views of the Department of Social Services, or indicate a commitment to a particular course of action. The Department of Social Services makes no representation and accepts no responsibility for the accuracy, reliability, currency or completeness of any materials (including third party materials) contained in this document.

Further, the Department of Social Services disclaims all liability to any person in respect of anything, and of the consequences of anything, done or omitted to be done by any such person in reliance, whether wholly or partly, upon any information presented in this document.

The Department of Social Services makes available materials in this document on the understanding that it is not providing professional advice. Before relying on any of the materials in this document, users should obtain appropriate professional advice.

Views and recommendations of third parties, which may also be included in this document, do not necessarily reflect the views of the Department of Social Services, or indicate a commitment to a particular course of action. Links to other internet sites are for your convenience. These links do not constitute endorsement of materials at those sites, or any associated organisation, product or service.

# MPower108 Operational action plan

| Plan type | Operational action plan - customer service goal 1. |
| --- | --- |
| Date | 30th June 2021. |
| Issue/strategy | Comments |
| 1 Meet goals and objectives for customer service as outlined in the MPower108 2021Strategic and Operational plan | Not having customer feedback recorded and implemented in all decisions is impeding our responsibility to our customers and the organisations competitive advantage. |
| 2 |  |
| 3 |  |

## Outcomes

| No. | Objectives | Measures of performance |
| --- | --- | --- |
| 1 | We (Mpower108) will provide accessible and affordable services that are responsive to the needs of the community. | Increase customer feedback by 10% by the end of June 2022 |

## Plan for achieving objectives

| Actions | Step by Step Plan | Due Date | Name | Completed date and signature |
| --- | --- | --- | --- | --- |
| Develop clear and consistent ways to hear the voice of our customers across the organisation and at a governance level | - Create approved position advertisement for a customer liaison officer. - Place advertisement on Job websites and send internal email alerting staff to a new role. | June 30-July 14th | Sydney Centre Manager Tammy White Rodney Cyan Frontline Leader Sydney HR manager Tracey Gold for approval. |  |
|  | - Investigate software options for customer feedback/reporting and performance metrics. - Analyse different options including Industry and IT Stakeholder consultation for input into best options. | June 30-July 14th | Sydney Centre Manager Tammy White Rodney Cyan Frontline Leader Sydney IT manager Head office. |  |
|  | - Conduct recruitment interviews, reference checks for new customer service liaison officer. | July 20-August 20th | Sydney Centre Manager Tammy White Rodney Cyan Frontline Leader Sydney HR manager Tracey Gold for approval. |  |
|  | - Obtain approvals for procurement and installation of Updates to software program for customer feedback, reporting and performance metrics. | July 20-August 20th | Sydney Centre Manager Tammy White Rodney Cyan Frontline Leader Sydney IT manager Head office. |  |
|  | - Recruit and induct F/T Customer liaison officer for customer feedback implementation | August 20th to September 14th | Sydney Centre Manager Tammy White Rodney Cyan Frontline Leader Sydney HR manager Tracey Gold for approval. |  |
|  | - Procure and install Updates to software program for customer feedback, reporting and performance metrics. | August 20th to September 14th | Sydney Centre Manager Tammy White Rodney Cyan Frontline Leader Sydney IT manager Head office. |  |
|  | - Staff development and training of obtaining and recording customer feedback Staff development and training of new software operations and processes. | August 20th to September 14th | Sydney Centre Manager Tammy White Rodney Cyan Frontline Leader Sydney HR manager Tracey Gold for approval. All Sydney centre employees expected to attend Sydney Centre Manager Tammy White Rodney Cyan Frontline Leader Sydney IT manager Head office. All Sydney centre employees expected to attend |  |
|  |  | XX/XX |  |  |
|  |  | XX/XX |  |  |
| Approval: | Name: Ahmed Best |  | 14/06/21 | Signature: Ahmed Best |