Diploma of Leadership in Disability Services – Copyright License and Disclaimer Notice

Copyright

Copyright in this document and all the information it contains vests in the Department of Social Services on behalf of the Commonwealth.

Copyright notice — 2023

This document BSBOPS504_Toolkit_2_Illustrative examples is licensed under the Creative Commons Attribution 4.0 International Licence

Licence URL: https://creativecommons.org/licenses/by/4.0/legalcode

Please attribute: © Commonwealth of Australia (Department of Social Services) 2023

Notice:

- If you create a derivative of this document, the Department of Social Services requests the following notice be placed on your derivative: Based on Commonwealth of Australia (Department of Social Services) data.

- Inquiries regarding this licence or any other use of this document are welcome. Please contact: Branch Manager, Communication Services Branch, Department of Social Services. Phone: 1300 653 227. Email: communications@dss.gov.au

Notice identifying other material or rights in this publication:

- Australian Commonwealth Coat of Arms — not Licensed under Creative Commons, see https://www.pmc.gov.au/government/commonwealth-coat-arms

- Certain images and photographs (as marked) — not licensed under Creative Commons

Disclaimer

This document is intended for educational purposes. The materials in the document may incorporate views, standards or recommendations of third parties or comprise materials contributed by third parties (third party materials). Such third party materials does not necessarily reflect the considered views of the Department of Social Services, or indicate a commitment to a particular course of action. The Department of Social Services makes no representation and accepts no responsibility for the accuracy, reliability, currency or completeness of any materials (including third party materials) contained in this document.

Further, the Department of Social Services disclaims all liability to any person in respect of anything, and of the consequences of anything, done or omitted to be done by any such person in reliance, whether wholly or partly, upon any information presented in this document.

The Department of Social Services makes available materials in this document on the understanding that it is not providing professional advice. Before relying on any of the materials in this document, users should obtain appropriate professional advice.

Views and recommendations of third parties, which may also be included in this document, do not necessarily reflect the views of the Department of Social Services, or indicate a commitment to a particular course of action. Links to other internet sites are for your convenience. These links do not constitute endorsement of materials at those sites, or any associated organisation, product or service.

# Illustrative examples

Illustrative example – Risk management CSF's

When managing current risks in human resources, your organisation will have a strategy in place which outlines the vision, mission and business objectives for risk management. Each of these relate to how this can help the organisation remain competitive in the disability sector.

For example, if MPower108 outlined a strategic goal of providing a safer working environment for all, the objectives specify to improve work health and safety for both workers and customers. The overall CSF (Critical Success Factors) could then be to lower workplace injury by 5% in the next three months.

This is a critical factor of success for this business area, and you will need to consider any risks that may impact on the achievement of this CSF. For example, what is the risk of increased staff dissatisfaction due to the fortnightly audits?

The risk action plan is to achieve this goal, objective and its applicable CSF by introducing fortnightly Work Health and Safety (WHS) audits. These goals, objectives, CSFs, and action plans are then communicated to staff who implement actions.

This example demonstrates how risk management activities support and promote the organisation’s vision, mission and business objectives, and relates this to other staff.

## Illustrative example – External analysis

When the Frontline Leader was asked to assess social influences on risk by conducting a PESTLE analysis for the MPower108 organisation, they came across the “social model for disability.” The social model for disability is now the internationally recognised way to view and address ‘disability’. The United Nations Convention on the Rights of Persons with Disabilities (CRPD) marks the official change in thinking in attitudes towards people with disability and approaches to disability concerns.

When the Australian disability sector decided to adopt this model over the traditional medical model for disability, it became an external factor which impacted all organisations in the sector, in particular the organisations’ policies and procedures.

The new social model for disability made the Frontline Leader consider how they would have managed risks when implementing this model, over the old medical model into the organisations policies and processes.

## Illustrative example – Communication plan

MPower108 follows a strict belief that communicating the risk management process to stakeholders can:

encourage input from stakeholders

develop a relationship with stakeholders.

However, the Frontline Leader will need to determine who needs to be involved in the risk management process and at which level. The organisation has created a risk communication plan outline for their internal and external stakeholders in the example below.

Table 1: Risk communication plan

| Risk communication plan template |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Communication | Description | Frequency (e.g., daily, weekly, monthly) | Format (email, phone, skype, meeting) | Owner | Recipient/Attendees |
| What type of communication? | Description of the contents/ purpose of this communication? |  |  | Who sends? | Who gets? |
| Report | Stakeholder’s report – to update on progress. | Weekly | Email | Manager | Team and external stakeholders |
| Proposal | Written using the organisations proposal template outlining suggestions for improvement | One off then monthly update | Email and meeting | Manager | Senior managers to approve |
| Feedback | A stakeholder feedback survey | Monthly then quarterly | Email and informal meetings | Manager | Team, external stakeholders and management |

Before the Frontline Leader completed the plan, they reviewed the MPower108 stakeholder matrix and the MPower108 communication plan, policies and processes, to gain a further understanding of how they are expected to communicate with stakeholders using these organisational policies and processes.

## Illustrative example – Identifying risks with stakeholders

MPower108 is building accommodation to provide residential care services. The key stakeholders come together in a meeting to discuss the risks for the building project and determine the following information:

What could happen? Theft could occur and building materials be stolen from site.

Why could it happen? If the site or after hour deliveries are not secure.

When might it happen? At night or over the weekend.

Where could it happen? On the building site.

How could it happen? It could be organised or random and opportunistic.

Once the key stakeholders understand the answers to the questions, steps can be taken to manage the outcome. The company can take steps to fully secure the site, monitor deliveries and contract a security business to patrol the sites especially overnight and weekends. Or they might choose to transfer risk by insuring properly.

Some of the documents you would use when collaborating with stakeholders is a meeting agenda, outlining points to be discussed in the meeting, and meeting minutes. The meeting minutes provide a transcript of what has been said in a meeting and by whom.

Access and review the MPower108 meeting agenda and meeting minutes templates to understand each document's role in recording communication with stakeholders.

## Illustrative example – Contingencies for risk treatment

The aim of contingency and containment is to overcome the effects of the risk as it impacts on the planning and outcomes. In their risk treatment decisions, the Frontline Leader had to consider MPower108 contingencies to risk treatment options for the purchase of a new mobility van. This van was purchased to be used when transporting customers to and from appointments.

Table 2: Contingencies developed from risk effect on this proposal

| MPower108 Risk contingencies |  |  |
| --- | --- | --- |
| Risk | Effect on project | Contingency (Examples only) |
| Vehicle specifications are returned late | The specifications will not be available at the scheduled time | Put pressure on to ensure specifications are returned Delay start date |
| Management does not approve finances | The proposal cannot commence until the manager has approved the purchase | Put extra effort into ‘selling’ the need for the van to management Delay start date Look for cost reducing options |
| Team is not available to drive the van at appointed times | The people nominated for certain tasks or activities will not be able to carry them out | Delay start times Have ‘back up’ team Reschedule tasks to allow for driving time |
| The ‘wet season’ may start early | Assisting customers to enter the van in wet slippery conditions will be a hazard | Carry out pre-work Do nonslip work on customers driveways Build wet-weather sheds and shelters at major in care facilities. |
| Van safety equipment is inappropriate | The proposal would stall if equipment needed for certain elements of the proposal is incorrect | Appoint team leader to ensure equipment is appropriate Put indemnity clause in purchase/lease contracts (noting this will not impact health and safety liability) Highlight ‘slack’ time in schedule for use if equipment is not correct |
| The van vendor may change their mind halfway through the transaction | The scope of the purchase may change with little or no warning | Put extra vendor meetings in communications management plan Maintain close monitoring and reviewing of progress to allow for sudden changes Warn work team about possibility of sudden changes Schedule critical work first Schedule major payments Include rigorous change management policy in contract and plan |
| Faults may not be picked up until late | The purchase will stall while we go back and fix up earlier faults | Ensure close monitoring and review of purchase progress Ensure team are committed Allow extra time in the schedule for finding and fixing faults Ensure purchase contract includes warranty and maintenance period |
| Sub-contractors who need to fit safety features such as ramps may make changes to contracts | Contract agreements may not be fulfilled at the scheduled time | Ensure contracts are agreed prior to work commencing and contain robust terms regarding performance Put indemnity clauses in contracts Have back-up schedule developed that allows for contracted work to be delayed Allow extra time in the schedule for completion of contracted work Allow extra funds in budget for over-contract payments |

## Illustrative example – Ignoring risks

An example of ignoring the risk might be that a MPower108 Frontline Leader knows that 10% of its staff will become unavailable at Christmas time. So, they offer limited Christmas services to customers at a reduced price, knowing that most of their customers will appreciate the option of skeleton support at a lower price. They have not acted to reduce or treat the risk but have made concessions.

Notably, depending on the risk being treated, there is the possibility of using several alternatives. For example, it may be an option to employ Christmas staff, offer higher wages to entice current staff to work over Christmas or train new staff up to take on more responsibilities. Although, all three methods would assist to treat the risk and could be used in isolation or in combination.

## Illustrative example – Risk action plan

Consider the action plan for two of the risks identified for MPower108. The first risk which was identified by the Frontline Leader is the poor allied health referral system, the second was the new access to an adjoining medical centre does not have wheelchair access.

An action plan provides a set of instructions to make sure the necessary steps are taken to deal with the risk and reduce impact. Therefore, the Frontline Leader considered the actions to be taken to treat the risks and who would be involved then added these to the MPower108 risk action plan.

Table 3: Risks

| Organisational Risks |  |
| --- | --- |
| Poor allied health referral system | Risk rating is Extreme. Take immediate steps to AVOID this happening and to remove the likelihood of this impacting on customer service. |
| New access to adjoining medical centre does not have wheelchair access. | Risk rating is High. Mitigate access issues via ensuring a qualified construction firm is engaged to manage disabled access |

Table 4: Risk action plan

| Organisational Risk action plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| Risk # from plan | What action is required | Who is responsible | Time frame | Date for review |
| Poor allied health referral system | Avoid – Take immediate steps to rectify allied health referrals for existing customers Review the entire referral program through regular meetings, email contact essential with stakeholders | Organisational manager and department managers Contract experts to analyse impact of changes to the system | Immediate | Within three months |
| New access to adjoining medical centre does not have wheelchair access. | Mitigate– Consult with construction company to request help with access, costs, and expert advice on how to minimise injury and damage to customers | Manager of the centre and Frontline Leaders on shift to liaise with the construction company | Begin discussions immediately to avoid delays and ensure early planning | Review in one month |
| Both | Mitigate – Consult outside experts and other stakeholders (government, council) as to right to insist on cooperation from medical facility and discuss possible alternative arrangements | Manager of the centre and Frontline Leaders on shift to liaise with the experts | Immediate in conjunction with above steps to avoid lost time |  |

## Illustrative example – Communicating processes to personnel

The MPower108 Frontline Leader has identified risks within the organisations customer reporting system.

A risk assessment of the reporting system finds the risk rating is Extreme. After much consultation, the decision made for the risk treatment is to take immediate steps to avoid this happening and to remove the likelihood of this impacting on compliance and customer service.

In consultation with relevant stakeholders and obtaining approvals from his centre manager, the Frontline Leader creates a risk management action plan outlining the tasks, roles, and responsibilities of each staff member.

The Frontline Leader emails the staff, requesting a meeting to outline this information to the team and relevant stakeholders.

## Illustrative example – Risk implementation and monitoring

Review the risk action or management plan for risks identified at MPower108. A risk action or management plan provides a set of instructions to make sure the necessary steps are taken to implement the risk actions and ensure they are monitored. The Frontline Leader has added to additional columns to the risk action plan which provides a straightforward way to monitor the implementation of each action. These two columns are to list the current controls and, in the review, determine if these controls are acceptable. The Frontline leader has completed the review in the predetermined time frames and made comments to the risk action plan as shown below.

Table 5: Organisation risks

| Organisation Risks |  |
| --- | --- |
| Poor allied health referral system | Risk rating is Extreme. Take immediate steps to AVOID this happening and to remove the likelihood of this impacting on customer service. |
| Lack of independent representative for compliance team | Risk rating is High. Mitigate access issues via ensuring a qualified representative is appointed to compliance team |

Table 6: Action plan review

| Organisation Risk action plan review |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Risk # from plan | Action implemented | Who is responsible | Time frame | Date of review | Current controls | Acceptable Y/N |
| 1 | Avoid – Take immediate steps to rectify allied health referrals for existing customers. Review the entire referral program through regular meetings, email contact essential with stakeholders. | Centre manager and department managers Contract experts to analyse impact of changes to the system | Immediate | Within three months Review 1. 17/12/20xx | Centre manager is reviewing the referral system for updates and rectification | Y |
| 2 | Mitigate– Consult with industry employment body to seek referrals for an independent rep to join the compliance team | CEO (Chief Executive Officer) | Begin discussions immediately to avoid delays and ensure prompt recruitment | Review in one month. Review 1 15/10/20xx | CEO has discussed the requirement for an independent representative with industry employment bodies who have provided a list of eligible applicants | y |