Diploma of Leadership in Disability Services – Copyright License and Disclaimer Notice

Copyright

Copyright in this document and all the information it contains vests in the Department of Social Services on behalf of the Commonwealth.

Copyright notice — 2023

This document MPower108 Risk contingencies example is licensed under the Creative Commons Attribution 4.0 International Licence

Licence URL: https://creativecommons.org/licenses/by/4.0/legalcode

Please attribute: © Commonwealth of Australia (Department of Social Services) 2023

Notice:

- If you create a derivative of this document, the Department of Social Services requests the following notice be placed on your derivative: Based on Commonwealth of Australia (Department of Social Services) data.

- Inquiries regarding this licence or any other use of this document are welcome. Please contact: Branch Manager, Communication Services Branch, Department of Social Services. Phone: 1300 653 227. Email: communications@dss.gov.au

Notice identifying other material or rights in this publication:

- Australian Commonwealth Coat of Arms — not Licensed under Creative Commons, see https://www.pmc.gov.au/government/commonwealth-coat-arms

- Certain images and photographs (as marked) — not licensed under Creative Commons

Disclaimer

This document is intended for educational purposes. The materials in the document may incorporate views, standards or recommendations of third parties or comprise materials contributed by third parties (third party materials). Such third party materials does not necessarily reflect the considered views of the Department of Social Services, or indicate a commitment to a particular course of action. The Department of Social Services makes no representation and accepts no responsibility for the accuracy, reliability, currency or completeness of any materials (including third party materials) contained in this document.

Further, the Department of Social Services disclaims all liability to any person in respect of anything, and of the consequences of anything, done or omitted to be done by any such person in reliance, whether wholly or partly, upon any information presented in this document.

The Department of Social Services makes available materials in this document on the understanding that it is not providing professional advice. Before relying on any of the materials in this document, users should obtain appropriate professional advice.

Views and recommendations of third parties, which may also be included in this document, do not necessarily reflect the views of the Department of Social Services, or indicate a commitment to a particular course of action. Links to other internet sites are for your convenience. These links do not constitute endorsement of materials at those sites, or any associated organisation, product or service.

# MPower108 Risk contingencies

| Risk | Effect on project | Contingency (Examples only) |
| --- | --- | --- |
| Vehicle specifications are returned late | The specifications will not be available at the scheduled time | put pressure on to ensure specifications are returned delay start date |
| Management does not approve finances | The proposal cannot commence until the manager has approved the purchase | put extra effort into ‘selling’ the need for the van to management delay start date look for cost reducing options |
| Team is not available to drive the van at appointed times | The people nominated for certain tasks or activities will not be able to carry them out | delay start times have ‘back up’ team reschedule tasks to allow for driving time |
| The ‘wet season’ may start early | Assisting customers to enter the van in wet slippery conditions will be a hazard | carry out pre-work do nonslip work on customers driveways build wet-weather sheds and shelters at major in care facilities. |
| Van safety equipment is inappropriate | The proposal would stall if equipment needed for certain elements of the proposal is incorrect | appoint team leader to ensure equipment is appropriate put indemnity clause in purchase/lease contracts (noting this will not impact health and safety liability) highlight ‘slack’ time in schedule for use if equipment is not correct |
| The van vendor may change their mind halfway through the transaction | The scope of the purchase may change with little or no warning | put extra vendor meetings in communications management plan maintain close monitoring and reviewing of progress to allow for sudden changes warn work team about possibility of sudden changes schedule critical work first schedule major payments include rigorous change management policy in contract and plan |
| Faults may not be picked up until late | The purchase will stall while we go back and fix up earlier faults | ensure close monitoring and review of purchase progress ensure team are committed allow extra time in the schedule for finding and fixing faults ensure purchase contract includes warranty and maintenance period |
| Sub-contractors who need to fit safety features such as ramps may make changes to contracts | Contract agreements may not be fulfilled at the scheduled time | ensure contracts are agreed prior to work commencing and contain robust terms regarding performance put indemnity clauses in contracts have back-up schedule developed that allows for contracted work to be delayed allow extra time in the schedule for completion of contracted work allow extra funds in budget for over-contract payments |