Diploma of Leadership in Disability Services – Copyright License and Disclaimer Notice

Copyright

Copyright in this document and all the information it contains vests in the Department of Social Services on behalf of the Commonwealth.

Copyright notice — 2023

This document BSBPMG430_Toolkit_2_Illustrative examples is licensed under the Creative Commons Attribution 4.0 International Licence

Licence URL: https://creativecommons.org/licenses/by/4.0/legalcode

Please attribute: © Commonwealth of Australia (Department of Social Services) 2023

Notice:

- If you create a derivative of this document, the Department of Social Services requests the following notice be placed on your derivative: Based on Commonwealth of Australia (Department of Social Services) data.

- Inquiries regarding this licence or any other use of this document are welcome. Please contact: Branch Manager, Communication Services Branch, Department of Social Services. Phone: 1300 653 227. Email: communications@dss.gov.au

Notice identifying other material or rights in this publication:

- Australian Commonwealth Coat of Arms — not Licensed under Creative Commons, see https://www.pmc.gov.au/government/commonwealth-coat-arms

- Certain images and photographs (as marked) — not licensed under Creative Commons

Disclaimer

This document is intended for educational purposes. The materials in the document may incorporate views, standards or recommendations of third parties or comprise materials contributed by third parties (third party materials). Such third party materials does not necessarily reflect the considered views of the Department of Social Services, or indicate a commitment to a particular course of action. The Department of Social Services makes no representation and accepts no responsibility for the accuracy, reliability, currency or completeness of any materials (including third party materials) contained in this document.

Further, the Department of Social Services disclaims all liability to any person in respect of anything, and of the consequences of anything, done or omitted to be done by any such person in reliance, whether wholly or partly, upon any information presented in this document.

The Department of Social Services makes available materials in this document on the understanding that it is not providing professional advice. Before relying on any of the materials in this document, users should obtain appropriate professional advice.

Views and recommendations of third parties, which may also be included in this document, do not necessarily reflect the views of the Department of Social Services, or indicate a commitment to a particular course of action. Links to other internet sites are for your convenience. These links do not constitute endorsement of materials at those sites, or any associated organisation, product or service.

# Illustrative examples

Illustrative example – MPower108 customer project

MPower108 is a disability service provider registered under the NDIS (National Disability Insurance Scheme). MPower108 operates four service centres, based in Sydney, Melbourne, Brisbane and Nambour. MPower108 provides services for Supported Independent Living (SIL) customers, operates day centres for customers and meets a variety of customer needs according to individual care plans.

One of the Melbourne customers, Zac Whittle, is under an NDIS funded care plan. Zac is 20 years old and holds a part time job. He receives in home support from MPower108 and has some mobility concerns. Zac has a physical condition which impedes his walking ability and can cause him to lose balance. He has NDIS funding for a ramp to be built with a handrail between the driveway and his home’s front entrance.

Senior Centre Manager, Carl White will be the project sponsor (or owner) and Frontline Leader, Toni Roberts, who has detailed knowledge of Zac’s needs will be managing it.

## Illustrative example – Gathering information

Carl has asked Toni to gather information required to scope Zac’s mobility project. Toni sources the following in preparing to scope the project:

MPower108 policies and procedures necessary for all project stages including communication policies, procedures and plan templates, delegations and authorities policies, risk management  templates and processes, strategic plans and procurement policies and procedures

Zac’s NDIS plan

Reports (especially “Lessons learned”) of similar renovations to customer dwellings. She finds reports of a similar length concrete pathway installed last year at a share house.

Itemised budgets and external quotes for similar work

Construction codes of practice and disability services code of conduct

WHS legislation

Building permits and licensing requirements

Feedback from carers and MPower108 staff involved in similar projects previously

## Illustrative example – Project goals, objectives and deliverables

Toni considers Zac’s mobility needs carefully by checking his NDIS funded plan. While the goal is to build a ramp and a handrail, unless the project scope specifies the benefits through identification of objectives, and outputs or evidence of the objectives through deliverables, it could be disastrous. Toni determines the main goal, the objectives (i.e., the benefits achieving the goal will bring) and deliverables (the tangible outcomes and expectations of meeting the goal and objectives):

Goal: A ramp and handrail is installed

Objectives:

Ramp facilitates ease of access for Zac between driveway and home entrance

Ramp and handrail enable ease of movement between driveway and home entrance

Use of ramp and handrail allow for independent movement

- Deliverables

Ramp and handrail is installed between the driveway and front entrance of Zac’s house

Ramp is concrete and handrail is steel / aluminium

Ramp is installed next to the three current steps

Access to handrail is shared between ramp and steps

Ramp and handrail are 1.5 metres long

Handrail is sturdy, easy to grip and is the same length as the ramp

Handrail is accessed from both the ramp and the current steps

Ramp is even with an easily managed incline

Ramp and handrail is built to specification and meets industry and safety codes

## Illustrative example – Project constraints

Toni considers the limitations or constraints to the mobility project for Zac and identifies the following:

Zac’s NDIS plan provides a $10000 budget for the ramp and handrail

The quality of the materials for the project will be limited by the budget

Contractor availability may not meet the project commencement and completion dates

Toni also considers events that might occur to hinder the success of the project and identifies these risks

Inclement weather affects project completion

Contractors falling ill or stopping work affects project completion

Supply chain issues post-COVID means a delay on material supplies

Increase in costs due supply and demand do not meet NDIS funding limit

Delay in receiving quotes

No available local suppliers of work as Zac lives in a regional town

Alternate entries to Zac’s house are unsuitable if front entrance is inaccessible during the project

## Illustrative example – Project scope elements

Toni prepares the following scope elements:

Table 1: Scope elements

| MPower108 Project scope |  |
| --- | --- |
| Elements | Details of the elements |
| Operation | Carl White |
| Project budget | $10000 |
| Timeframe | 15/07/xx – 15/08/xx |
| Background | Customer, Zac Whittle, has mobility issues. The stairs between the driveaway and front entrance of his home have no handrail. Zac is unable to negotiate these steps without the physical support of his family and carer. |
| Goals | Install a ramp and handrail |
| Objectives | Ramp facilitates ease of access for Zac between driveway and home entrance Ramp and handrail enable ease of movement between driveway and home entrance Use of ramp and handrail allow for independent movement |
| Deliverables | Ramp is installed between the driveway and the front entrance of the home Ramp is concrete and handrail is steel / aluminium Ramp is installed next to the three current steps Access to handrail is shared between ramp and steps Ramp and handrail are 1.5 metres long Handrail is sturdy, easy to grip and is the same length as the ramp Handrail is accessed from both the ramp and the current steps Ramp is even with an easily managed incline Ramp and handrail is built to specification and meets industry and safety codes |
| Inclusions | A concrete ramp A steel / aluminium handrail |
| Exclusions | Repair of driveway excluded Resurfacing / repair of concrete at front entrance excluded Replacement or repair of three steps between driveway and home entrance excluded |
| Constraints | Budgetary limits, according to NDIS plan Timeframe to complete work Quality of materials used |
| Preliminary Risk Factors | Lack of available builders/labourers Delays in supplying quotes Inclement weather delays work completion Delay in supply of materials post-COVID Increase in costs since NDIS funding approval |
| Reporting Structure | a) Carl White b) Project owner c) 15/07/xx Monthly As per MPower108 Delegations and authorities policy and procedures |
| Sponsored by | COO Ahmed Best |
| Submitted by | Toni Roberts 01/06/xx |
| Authorised by | C White 10/06/xx |

## Illustrative example – Resourcing

Toni considers the financial, human and physical resources required for the project. Financial resourcing will come from Zac’s NDIS plan. Toni needs to manage Zac’s NDIS funding carefully. Funding under Zac’s plan was approved nearly a year ago. Since then, labour and material supply costs have escalated. Financial constraints will affect what can be performed under the current funding, and what may need to wait until next year.

Toni also considers human resourcing, and the time spent as overseer to the project. Allocating additional human resources to the project cannot come at the expense of allocations to other customers. Toni discusses this with her centre manager who considers reallocation of role responsibilities during the life of the project.

While the physical resources will be provided by the contractor, materials have lengthy delays and costs have increased. To keep within the budget, Toni negotiates with a local hardware store who has donated $500 in gift cards for the project.

## Illustrative example – Project stakeholders

The mobility project for Toni’s customer, Zac, involves those within MPower108 and external to the organisation. Toni does not yet know who will supply and install the ramp and handrail. This doesn’t stop her from preparing a matrix of the key stakeholders involved in the project.

Table 2: Stakeholder matrix

| Stakeholder Matrix / Register |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Customer name: |  | Zac Whittle |  |  |  |
| Customer File No: |  | 20070ZW |  |  |  |
| Role of stakeholder | Name of stakeholder |  | Contact details | Preferred method of communication | Important notes such as contact times / confidentiality etc |
| Project Sponsor | Carl White MPower108 Senior Centre Manager |  | c.white@mpower108.com 0408593487 | email / phone | Unavailable by phone prior to 1000 Responsible for planning project in consultation with project manager |
| Project Manager / Lead | Toni Roberts MPower108 COO |  | t.roberts@mpower108.com 0412957156 | email / phone / text | Responsible for planning the project, resource management, communication with stakeholders, managing risks and change, assigning and tracking tasks, creating schedules |
| Project Finance Officer | Michael Silver MPower108 |  | m.silver@mpower108.com 0419347985 | email | Arranging invoice payments, tracking project budget (in consultation with project manager) |
| Customer / client (external) | Zac Whittle Mona Whittle |  | zacs123@gmail.com 0406158963 mona987@gmail.com 0415297300 | phone / text phone / email / text | Works outside his home M-F 9 am – noon. Attends Hub centre each Sat 9 am – 2 pm. Lives with Zac Works M-F 8 am – 3 pm |
| Occupational Therapist (external) | Noela Jackson |  | noelajackson@bddalliedhealth.com 0415697852 | phone / email | available M-F 8 am – 5 pm Will consult with Project Manager regarding specifications of project to meet customer needs |
| Disability Support Worker | Alex Brennan |  | a.brennan@mpower108.com 0412981633 | phone / text / email | Provide support to Zac before, during and following project |
| Contractor / supplier (external) | to be confirmed |  | to be confirmed | phone / text / email | Provide project deliverables as per specifications and contract |

## Illustrative example – Stakeholder consultation

Toni thinks about the important stakeholders for the mobility project for Zac. Some stakeholders may need to be more involved in consultations than others. Zac is the critical stakeholder in the project and unless his needs are met, the project will fail. Zac’s mother, Mona, has first hand knowledge of the difficulties Zac has negotiating the steps from his driveway - she is often the person physically supporting him. Zac’s OT, Noela also knows Zac’s challenges and will be instrumental in consulting with the works contractor about the necessary specifications.

Project sponsor, Carl White may not need to be involved in every consultation. He will rely on Toni to report on communication outcomes and progress and can step in to assist in problem solving beyond Toni’s authority.

Some stakeholders will be consulted during all project stages, others less so.

Toni also considers how best to consult and communicate with stakeholders. Some, such as internal stakeholders, prefer email, which is useful when accompanied by a progress report, for example. Many contractors do not access their emails during the day, so should be consulted in person or by phone.

Toni will need to juggle many forms of consultation and communication throughout this project.

## Illustrative example – Delegations and authority

NDIS has provided $10000 to fund a ramp and handrail under Zac’s plan. Toni has received three quotes from contractors. The date for the commencement of work has already passed, as Toni had to chase up quotes. She has been advised that the quickest the work can be completed is one week, depending on a range of factors.

Quote 1 is within budget at $9850, however there could be a six-month delay on material supplies and the contractor is booked solid with work for the next four months. He quoted using a cheaper grade concrete and believes he can still complete the job within the NDIS funded period

Quote 2 is $11000 using better quality products than Quote 1 and the contractor has advised a one-month delay on material supplies. He can start the work when the materials arrive in a month.

Quote 3 is $10500 from a city contractor who is a two hour drive away. He will be charging additional for travel time and mileage and will take twice as long to complete the work as a result. He can start the job immediately.

Toni does not have the delegation and authority to award the work. She first phones Zac and arranges to come around to his home when Mona is also there to discuss the reasons for the delay in commencing the work. Toni also emails the specifications in the quotes to OT, Noela Jackson to ensure each meets Zac’s mobility needs. Toni discusses the options with Senior Centre Manager who has the approval authority. Finally, Toni phones Zac’s DSW, Alex, to advise on the progress to date. Alex does not need to do anything on the project yet, but will benefit from being kept informed as he provides Zac’s usual support.

## Illustrative example – Action plan

There are several activities taking place within the ramp project and Toni coordinates these tasks to help ensure they are completed on time and within budget.

Table 3: Action plan

| MPower108 Action plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Personnel responsible | Expected completion date | Cost ($) | Success indicator Performance metrics |
| Award contract of work | Centre Manager | 18/06/20XX | N/A | Contract is approved, signed and finalised |
| Risk / WHS assessment of alternate home access | OT | 18/06/20XX | $200 | Risk / WHS assessment completed and approved |
| Install ramp and handrail | Contractor / builder | 18/10/20XX | $9850 | Work is complete as per specifications and contract. |
| Train Zac on safe use of ramp and handrail | OT | 20/10/20XX | $200 | Zac uses the ramp and handrail safely and independently |

## Illustrative example – Communication plan

Toni has developed the following communication plan during the project’s life:

Table 4: Communication plan

| MPower108 Communication plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name: Communication plan for Zac Whittle project (ramp + handrail) |  |  |  |  |
| Communication goals |  |  |  |  |
| 1. Broadcast project objectives and achievements across Sydney centre team |  |  |  |  |
| 2. Update key stakeholders on project progress |  |  |  |  |
| 3. Obtain review / feedback |  |  |  |  |
| Goal | Owner | Audience | Channel | Date/Frequency |
| 1. Broadcast project objectives | CW | Sydney centre (all teams) | 1. Announcement email 2. Team meeting (Toni Roberts’) | 18/6/xx |
| 2. Progress updates | TR | Key stakeholders | Email | Every week |
| 3. Explain project benefits | CW | Key stakeholders | Stakeholder meeting (online) | Project kickoff 20/6/xx |
| 4. Customer feedback | TR | Toni’s team OT & Toni | 1. Survey (online) 2. Interview (in person) | 20/10/xx 21/10/xx |

## Illustrative example – Training plan

While Zac may be familiar with using ramps, in the interest of safety, he should be provided with training on navigating the ramp safely at home. As part of his contract, the builder will provide a 30 minute session instructing Zac with his OT, Noela present. Noela will then provide further instruction to Zac’s mother, Mona and his DSW, Alex, who may need to provide additional support until he can negotiate the ramp on his own.

Toni prepares a training plan as follows:

Table 5: Training plan

| MPower108 Training plan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Training plan for Zac Whittle project (ramp + handrail) |  |  |  |  |  |
| Training objectives / outcomes |  |  |  |  |  |
| 1. Zac can navigate the ramp safely using the handrail |  |  |  |  |  |
| 2. Care providers can offer safe support of the ramp if required |  |  |  |  |  |
| Method | Trainer | Audience | Time frame | Resources | Cost |
| Coaching | Contractor | OT and Zac | 30 minutes | Safety signage | N/A |
| Coaching | OT | Zac, Mona, DSW | 30 minutes | Safety signage | $100 |

## Illustrative example – Managing risk

Senior Centre Manager, Carl, has tasked Frontline Leader, Toni with developing a contingency plan with risks associated with the project as part of managing risks responsibly. Toni develops the following contingencies:

Table 6: Contingency plan

| MPower108 Contingency plan |  |  |
| --- | --- | --- |
| Risk | Effect on project | Contingency (Examples only) |
| Quotes are not submitted | Awarding of contract and commencement of project is delayed | Put pressure on contractors to ensure quotes are submitted Delay start date |
| Quotes are higher than customer’s NDIS funding | Project cannot commence unless within approved funding | Source alternate contractors Amend specifications (e.g., quality) Complete project in parts, across two funding periods |
| Materials are unavailable | Project cannot commence until materials are available | Look for alternate suppliers within budget Delay start date |
| Inclement weather | Project delays | Delay start times Reschedule tasks to allow for poor weather |
| Unavailable contractor (e.g., unwell, booked elsewhere) | Those nominated for certain tasks or activities will not be able to carry them out | Contractor appoints qualified labourer/s to continue work |
| Contractor may change their mind halfway through the transaction | The scope of the purchase may change with little or no warning | Schedule extra contractor meetings in communications management plan Maintain close monitoring and reviewing of progress to allow for sudden changes Warn customer about possibility of sudden changes Schedule critical work first Schedule major payments Include rigorous change management policy in contract and plan |
| Installation faults may not be picked up until late or installation does not meet WHS legislation | Project will stall while earlier faults are rectified | Ensure close monitoring and review of installation progress Ensure contractor is committed Allow extra time in the schedule for finding and fixing faults Ensure purchase contract includes warranty and maintenance period Delay payments until faults are rectified and WHS inspection report is completed and certified |

## Illustrative example – Manage creeping scope

Toni worked on an IT rostering project in a previous position which delivered at double its initial budget. Needs changed throughout the project which required significant customisation of the software and additional functionalities developed outside the original project scope.

As the budget allocated through Zac’s NDIS plan is fixed, Toni must avoid scope creep and keep to the original deliverables. Toni considers what might cause scope creep in the ramp and handrail project and develops strategies to manage it.

Table 7: Manage scope creep

| Mower108 Scope creep |  |  |
| --- | --- | --- |
| The cause | The impact | The strategy |
| Imprecise language with a lack of detail in describing the work | Poor quality work, including incomplete work or rework Delays in clarifying intent Open to interpretation Assumptions made Any outcome will be a good outcome Subjective choices made | Glossary of terms Drawings Detailed specification Contracts Third-party review Write in plain English Draft version of the scope Technical experts to review the schedule |
| Widely inaccurate estimates (time and cost) | Schedule delays and cost over-runs Pressure from stakeholders to stick with original estimates (deemed to be accurate) | An understanding that early estimates are exactly that – estimates Time to revise and fine-tune the schedule and costing Access to technical specialists with estimating experience |
| Failing to get third-party review | Insufficient detail Key parts omitted No insight from external parties | Distribute to qualified project personnel for review |
| No pattern, structure or chronological order | Chaotic schedule High chance of rework Conflicting resource assignments Impossible delivery timetable | Sequence the work logically Work backwards to check the logic Prototype the schedule Identify scheduling errors |
| Omitting special instructions and/or ignoring them | Non-compliance Workplace health and safety issues Possibility of rework Fast-tracking completion times Non-compliance Cost variations | Detailed technical specifications All supporting documentation is submitted Statutory requirements Third-party review |
| Lack of customer involvement | Imprecise requirements Delays with rework Delays in issuing completion certificates | Get the customer involved in the scoping stage Ensure project meetings include the customer |
| Insufficient planning time | Development of an ad hoc schedule At the mercy of unanticipated changes | Support the planning process and the time required Consider the consequences of poor planning Review previous projects that were poorly planned |
| Unavailability of resources | Delays in work Inferior resource replacements Cost variations Impact on morale and motivation | Secure written commitments from contractors Identify replacement resources |

## Illustrative example – Project sign-off

The contractor has advised project manager, Toni, the work has been completed and is requesting the final invoice payment. Before this can occur, Toni will submit an MPower108  Project completion template for sign-off as follows:

Table 8: Project completion form

| MPower108 Project completion |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Required Date | Responsible Person | Notes | Completed (Yes / No/ not needed) |
| Confirm deliverables |  |  |  |  |
| Testing of ramp / handrail | 2/11/xx | Customer, OT |  |  |
| Inspection report | 3/11/xx | Toni Roberts | In conjunction with Safety Officer |  |
| Safety certification | 2/11/xx | Contractor | Must be authenticated |  |
| Walk-through / training | 3/11/xx | Contractor, OT (Noela Jackson) | OT to train support worker and parent |  |
| Scope deliverables itemised, compared and checked* | 10/11/xx | Carl White, Toni Roberts |  |  |
| Identify outstanding work | 10/11/xx | Carl White |  |  |
| Sign-off agreed by Project Sponsor | 12/11/xx | Carl White |  |  |
| Sign-off agreed by customer | 12/11/xx | Zac Whittle |  |  |
| Sign-off agreed by other stakeholder (OT) | 12/11/xx | Noela Jackson |  |  |
| Worksite clear of rubbish, equipment and other WHS hazards | 3/11/xx | Contractor |  |  |
| Financials |  |  |  |  |
| Ensure all third party invoices are submitted | 15/11/xx | Carl White |  |  |
| Pay all contractors | 20/11/xx | Michael Silver |  |  |
| Pay all suppliers | 20/11/xx | Michael Silver |  |  |
| Ensure time sheets/logs up-to date | 20/11/xx | Michael Silver |  |  |
| Claim any in kind or co-contribution amounts related to funding | 20/11/xx | Michael Silver |  |  |
| Financial report completed (budget vs actual expenditure)* | 20/11/xx | Carl White, Michael Silver |  |  |
| Close books | 20/11/xx | Michael Silver |  |  |
| Lessons learned |  |  |  |  |
| Review and evaluate | 25/11/xx | Carl White, Toni Roberts |  |  |
| Lessons learned meeting | 25/11/xx | Carl White, Toni Roberts |  |  |
| Data collection for review/evaluation of project | 20/11/xx | Carl White |  |  |
| Documented* | 28/11/xx | Toni Roberts |  |  |
| Archive |  |  |  |  |
| Project documentation | 30/11/xx | Carl White |  |  |
| Project final report | 30/11/xx | Carl White |  |  |
| Notify and report |  |  |  |  |
| Notify stakeholders other than Sponsor and Team Members (OT) | 30/11/xx | Carl White |  |  |
| Stakeholder debrief meeting | 02/12/xx | Toni Roberts |  |  |
| Reassign team members | 02/12/xx | Toni Roberts |  |  |
| Give feedback to team members | 05/12/xx | Carl White |  |  |
| Conduct final project meeting (debrief team members) | 05/12/xx | Carl White |  |  |
| Ongoing maintenance or handover to customers | 05/12/xx | Carl White, Toni Roberts |  |  |
| Prepare final report (may include *items above | 05/12/xx | Carl White |  |  |